## Feuil1
ID | Feature | Requirement | User story | Priority | Status | DoD Checklist Met? | Comments
1 | Algorithm to classify operation states | Identification of operation periods and working segments. | As a production engineer, I want to visualize working segments on a timeline so that I can easily understand when the machine is active. | Must | Done | Yes | Logic finalized in S4 (Idle/Low/Int/High) based on activity score and statistical thresholds (14 & 20).
2.1 | Detection of the diferents programs of each machine | Energy consumption per program | As a factory manager i want to know the consumption for each cnc program to evaluate the efficiency | Should | To do | No | Focus has been on general activity states so far; specific program detection not explicitly detailed in S4.
2.2 | Energy estimation algorithm |  |  | Must | In progress | No | Started in S4. Raw variable (630) converted to kWh. Correlation with states to be finalized in S5. | Must | To do | Yes
3 | Pattern recognition algorithm | Repeated sequence detection | As a production engineer, i want to detect repeated operation sequences so that i can identify recurring patterns | Must | To do | No | Not addressed in Sprints 1-4.4.1 | Should | In progress | No
4.1 | Global dashboard | UI for visualization | As a user i want to interact with an interface that is easy to understand and that shows machine activity, alerts and energy data clearly. | Must | Done | Yes | Interface is now a realistic MVP connected to real database (2020-2022) with dynamic filters.
4.2 | Timeline with operation periods |  |  | Must | Done | Yes | Timeline selection works effectively with real dataset and date range pickers.
4.3 | Energy and consumption charts |  |  | Must | In progress | No | Basic visualization initiated (kWh conversion). Integration into main interface planned for S5.
4.4 | Alerts section |  |  | Must | Done | Yes |  | Could | Blocked
5.1 | Alerts detection algorithm | Determine and contextualize alerts | As a factory manager, I want to see all machine alerts classified by type and location, so that I can quickly understand issues, their causes, and take corrective actions. | Must | Done | No | SQL queries optimized based on finalized logic. "Critical Alarms" filtering rules established. | Won't | Done
5.2 | Classification of the diferent type of alerts |  |  | Must | In progress | No | "Critical Alarms" determined, but final validation of the list and metadata with the client is required in S5.