## Backlog
SPRINT : |  | 1 | Sprint goal | Define interface requirements, implement the first requirement "display operational status" on the data layer, and initiate backend structure.
FROM : |  | 2025-09-29
TO : |  | 2025-10-13
ID | Product Backlog ID | User Story / Task | Description | Owner | Priority | Status | Notes / Blockers
1.1 | N/A | Data Environment Setup | Setup of data extraction and cleaning environment. | Data Team | High | Done | Efficient workflow reported. | Must | To do | Yes
1.2 | 1 | Relevant Day Logic | Implemented Method 1 (max records) and Method 2 (deciles) to select representative days. | Data Team | High | Done | Method 2 is considered robust and representative. | Should | In progress | No
1.3 | 1 | Machine State Detection (v1) | Initial proposal using 6 variables and dynamic thresholds to detect Working/Idle states. | Data Team | High | Partial | Limited robustness; need to test with more variables. | Could | Blocked
1.4 | 4.1 | Backend Initialization | Start working on backend structure. | Backend Team | Medium | Postponed | Postponed until the data layer stabilizes. | Won't | Done