## Backlog
SPRINT : |  | 2 | Sprint goal | Refine data analysis and machine state detection methods, document the interface requirement.
FROM : |  | 2025-10-13
TO : |  | 2025-10-26
ID | Product Backlog ID | User Story / Task | Description | Owner | Priority | Status | Notes / Blockers
2.1 | 1 | Machine State Detection (v2) | New logic with 16 variables, "activity_score," and Elbow method for threshold determination. | Data Team | High | Done | Method is more stable and interpretable. | Must | To do | Yes
2.2 | 4.1 / 4.2 | Interface Requirements Doc | Creation of a detailed document defining all interface requirements and backend responses. | UI/UX Team | High | Done | Some requirements deemed too ambitious. | Should | In progress | No
2.3 | 4.1 | UI Mockups | Creation of visual prototypes/mockups. | UI/UX Team | Medium | Partial | Started late, limiting feedback opportunities. | Could | Blocked