## Backlog
SPRINT : |  | 3 | Sprint goal | Prototype the user interface and implement the first version of the backend to expose machine-state data.
FROM : |  | 2025-10-27
TO : |  | 2025-11-11
ID | Product Backlog ID | User Story / Task | Description | Owner | Priority | Status | Notes / Blockers
3.1 | 4.1 | Streamlit Prototype | Creation of functional prototype (KPIs, charts, filters) with demo data. | UI/UX Team | High | Done | Feedback: Clear and visual. | Must | To do | Yes
3.2 | 4.1 / 4.2 | Backend API v1 | Python backend setup (PostgreSQL) and first API route for total hours per state. | Backend Team | High | Partial | Data format correct, but responses are too slow. | Should | In progress | No
3.3 | N/A | Git & Streamlit Setup | Streamlit setup and Git repository structure established. | Dev Team | Medium | Done | Ready for integration in next sprint. | Could | Blocked