## Feuil1
SPRINT : |  | 4 | Sprint goal | Prototype the user interface and implement the first version of the backend to expose machine-state data (Focus on real data & optimization).
FROM : |  | 2025-11-12
TO : |  | 2025-11-24
ID | Product Backlog ID | User Story / Task | Description | Owner | Priority | Status | Notes / Blockers
4.1 | 4.1 / 4.2 | Real Data Integration | Connect Streamlit to real DB (2020-2022) and implement dynamic date pickers. | Frontend Team | High | Done | Connection stable, filters effective. | Must | To do | Yes
4.2 | 4.4 / 5.1 | Alarm Backend & Optimization | Optimize SQL queries and implement alarm visualization logic. | Backend Team | High | Done | Slowness issues from S3 resolved. | Should | In progress | No
4.3 | 1 | Machine State Logic (Final) | Finalize logic (Idle/Low/Int/High) based on statistical thresholds (14 and 20). | Data Team | High | Done | Logic finalized and validated. | Could | Blocked
4.4 | 2.2 / 4.3 | Energy Monitoring Init | Convert variable 630 (% to kWh) and compute consumption for relevant days. | Data Team | Medium | Partial | Need to associate consumption with machine states.
4.5 | N/A | Config Management | Create Config.yaml to hide configurations from public view. | Backend Team | Low | Done | Needs to be shared with the rest of the team.